## Instructions
EV Charger Risk / Hazard Matrix for CNSWJO Electric Vehicle Charging Toolkit
About | The EV Charger Risk/Hazard matrix will help you identify the main risks and how to minimise them across the following categories: ∙ Financial ∙ Safety ∙ Business Productivity ∙ Operational ∙ Reputational ∙ Legal/Regulatory
Who the tool is for? | For all parties in the planning phase of electric vehicle charging station installation, including businesses, councils, commercial operators and installers.
How to use the tool | The table lists common potential points of failure and known vulnerabilities of charging station infrastructure. Read table from left to right. Each risk is given a rating that is a function of the consequence and likelihood of threats occurring. Make sure to consider the impact that each consequence may have on your business. A treatment for each risk is proposed with corresponding reduction in risk. Consider the feasibility of each treatment for your installation.
Process
Process
Step 1 – Identify what process you are reviewing
Step 2 – Use 'Table' tab to Identify the enablers that make this process occur
Step 3 – Reading from left to right on 'Table' tab, understand whether mitigating factors are required for your project
Step 4 – Consider Risk Treatment Plan using examples from 'Table' tab for guidance and review residual risk against risk appetite
Updated 18/03/20

## Table
Asset ID | Common potential points of failure and known vulnerabilities | Phase | Threat Type | Threat sources | Current Risk Consequence | Consequence Category | Likelihood | Risk Rating | Treatment | Detail | New Risk Rating
EVSE Electrical Site People (organisational) People (user) Business | Description | Installation Operation | Malicious Accidental Negligence Natural/environmental | Internal External | Catastrophic Major Moderate Minor Insignificant | Financial Safety Business Productivity Operational Reputational Legal/Regulatory | Almost Certain Likely Possible Unlikely Rare | Low Medium High Extreme | Accept Avoid Transfer Reduce |  | Low Medium High Extreme
Electrical | Electrical fault | Installation | Negligence | Internal | Catastrophic | Safety | Rare | Medium | Transfer | Outsource installation to contractor | Low
Electrical | Blackout | Operation | Natural | External | Moderate | Business Productivity | Unlikely | Medium | Accept (Option to reduce) | On-site batteries | Low
EVSE | Hardware malfunction | Operation | Accidental | External | Minor | Operational, Reputational | Rare | Low | Reduce | Choose reputable EVSE manufacturer | Low
EVSE | Hardware damage by car | Operation | Accidental | External | Minor | Operational | Possible | Medium | Reduce | Install physical barriers such as bollards, tyre stops | Low
EVSE | Hardware vandalised | Operation | Malicious | External | Moderate | Business Productivity, Operational | Unlikely | High | Reduce | Install security lighting and CCTV Install additional EVSE for redundancy | Low
EVSE | Software bug | Operation | Negligence | External | Minor | Business Productivity, Operational | Unlikely | Medium | Reduce | Regular testing of system | Low
EVSE | Network failure/offline | Operation | Accidental | External | Moderate | Business Productivity, Operational, Reputational | Rare | Low | Reduce | Ensure chargers default to "dumb" operation | Low
People (user) | User data leak | Operation | Malicious | External | Moderate | Reputational, Legal/Regulatory | Unlikely | Medium | Reduce | Ensure user data is stored securely | Low
People (user) | User error | Operation | Accidental | Internal | Major | Safety | Unlikely | Medium | Reduce | Provide clear instructions and warning signage | Low
Business | Underutilisation | Operation | Environmental | External | Moderate | Financial, Reputational | Likely | High | Accept | Accept that short term returns will be negligible | High
Site | "ICEing", whereby non-EV are blocking charging station | Operation | Malicious | External | Moderate | Operational, Business Productivity | Possible | High | Reduce | Clear signage, regulation of car space use (penalties) | Medium
Site | Vehicle compatibility error | Operation | Negligence | Internal | Minor | Business | Unlikely | Medium | Reduce | Update firmware regularly | Low
Site | Congestion | Operation | Environmental | External | Moderate | Operational, Reputational | Possible | High | Accept | Use during peak times (long weekends) may congest the system, leading to user frustration. | High
Site | Bushfire | Operation | Environmental | External | Moderate | Financial,Safety, Operational, Business Productivity | Unlikely (location dependent) | Medium | Avoid | An on site battery may provide emergency charge in the event that power is cut off. Ensure site is surrounded by fire break. EV chargers can help in the event of natural disasters. | Low
Site | Flood | Operation | Environmental | External | Moderate | Financial,Safety, Operational, Business Productivity | Unlikely (location dependent) | Medium | Avoid | Do not install in flood zone. EV chargers can help in the event of natural disasters. | Low
Site | Dust | Operation | Environmental | External | Insignifacant | Operational | Unlikely | Low | Reduce | Ensure site is cleaned regularly | Low
Site | Rain/hail/snow | Operation | Environmental | External | Minor | Operational, Safety | Possible | Medium | Reduce | Provide cover for charge station. | Low

## Threats
Threat sources
Trusted Sources with Malicious Intent – T1
Trusted Sources without Malicious Intent – T2
External Sources with Malicious Intent – T3
External Sources without Malicious Intent – T4
Environmental – T5

## Likelihood
Likelihood Descriptor | Likelihood Description Statements
Almost Certain | The event is EXPECTED to occur in most circumstances.
Likely | The event will PROBABLY occur in most circumstances and is expected at some time.
Possible | The event MIGHT occur at some time but is not expected.
Unlikely | The event COULD occur at some time.
Rare | The event MAY occur in exceptional circumstances.

## Consequence
Consequence Descriptor | Financial | Safety | Business Productivity | Operational | Reputation | Legal Regulatory
Catastrophic | Possible loss >$40k | Permanent injuries/deaths | Catastrophic impact on operations | Supply disrupted > 100% customers Major Failure to entire Grid Black Start | Extended media coverage; major government embarrassment or loss of public support; public enquiry Removal of CEO | Loss of operating licence or directors/senior management charged and convicted
Major | Possible loss $16k - $40k | Permanent injury/stress | Failure of one or more key organisational objectives leading to major disruption | Supply disrupted > 50% customers Major Failure to parts of the Grid | Heavy media coverage; government embarrassment or loss of public support. | Inquest in to business resulting in an enforcement order fine and court conviction
Moderate | Possible loss $4k - $16k | Injury requiring medical treatment / long term incapacity. | No threat to achievement of objectives but could result in some moderate disruption | Supply disrupted > 20% customers From a single event | Customer comments escalated to management; minor media coverage. | Likely fine or prosecution. Administrative undertaking
Minor | Possible loss $1k - $4k | Injury requiring first aid treatment / temporary loss of time. | Minor reduction in effectiveness and efficiency for a short period | Supply disrupted to < 10% customers for less than 1 week | Adverse customer comments | Warning issued by regulator
Insignificant | Possible loss <$1000 | Injury resulting in no loss of time | Negligible impact to effectiveness and efficiency | Supply disrupted to < 1% customers for less than 1 day | Manageable adverse customer comments | No legal or regulatory consequence.

## Risk
Consequence
|  | Insignificant | Minor | Moderate | Major | Catastrophic
Likelihood | Rare | Low | Low | Low | Medium | Medium
| Unlikely | Low | Medium | Medium | Medium | High
| Possible | Low | Medium | High | High | High
| Likely | Medium | Medium | High | High | Extreme
| Almost Certain | Medium | High | High | Extreme | Extreme

## Risk ExposureAcceptance
Risk Rating | Responsibility for Risk Acceptance | Action
Extreme | Board; CEO | Would be expected to seriously damage the organisation’s ability to continue to operate with the confidence of its customer base or corporate owners. Could result in serious social or economic damage and may affect the organisation’s ability to continue operations.
High | CEO; Executive; Risk Manager | Would be expected to have a significant impact on corporate budgets and organisational reputation. Could lead to extended service disruption and seriously inconvenience or have health impacts on a wide section of the customer base.
Medium | Risk Manager Senior Manager | Likely to result in short term, localised, disruption to services and require escalation through line management. Could generate localised adverse media comment and moderate penalties or costs unable to be borne via normal operational budgets.
Low | Risk Manager Senior Manager | Unlikely to have an impact that could not be satisfactorily dealt with via normal operational procedures.
Action | We need to determine the responsibility hierarchy for this project

## Risk Treatment
Risk Treatment | Description
Accept | do nothing and accept the current level of evaluated risk;
Avoid | cease doing the business activity that brings about the possibility of the threat occurring;
Transfer | pass the responsibility for implementing mitigating controls to another entity. Responsibility for threat and risk management remains the responsibility of the organisation, and
Reduce | implement controls to reduce risk to an acceptable level.

## Process
Process
Step 1 – Identify what process you are reviewing
Step 2 – Use 'Table' tab to Identify the enablers that make this process occur
Step 3 – Reading from left to right on 'Table' tab, understand whether mitigating factors are required for your project
Step 4 – Consider Risk Treatment Plan using examples from 'Table' tab for guidance and review residual risk against risk appetite